## Slide 1
Industry/University Cooperative Research Center (I/UCRC)
Advanced Mammalian Biomanufacturing Innovation Center (AMBIC)
Contents are Proprietary to AMBIC and its Members
Terms of Center Membership Agreement Apply
Develop an Inducible Stable Producer Cell Line for rAAV Production via Site-Specific Integration
Qiang Fu and Emily Doleh
Seongkyu Yoon (PI) / Mark Blenner (Co-PI)
Mentor Meeting – April 17, 2023
A National Science Foundation-facilitated
academic – industry – government consortia
to advance precompetitive knowledge in biomanufacturing
www.ambic.org

## Slide 2: Agenda
Project overview
UD Progress
  Plasmid design and timeline for assembly
UML Progress
Action Items

## Slide 3
Industrial Relevance & Need
Drawbacks of the traditional rAAV production process that uses transient transfection in HEK293 cells
Complicated and expensive process consuming considerable amount of transfection reagent and plasmids
The lot-to-lot variation of the products
Difficult to scale up
HEK 293 cells
A stable producer of rAAV is needed!

## Slide 4
Objectives
Refactor rAAV rep, cap, and helper genes using variations of the inducible Tet-off promoter
Optimize the rAAV rep, cap, and helper gene expression levels for high titer rAAV, by Kozak sequences and degrons
Establish an inducible stable producer cell line with site specific integration in well-known human genomic safe harbors for rAAV production
Project Goals
Design inducible circuits that can regulate the timing and level of gene expression for all components necessary to make rAAV
Develop an inducible stable producer cell line with site-specific integration for extensible rAAV production
Notes: Why Tet-off promoter rather than Tet-on?
The tet-off-based inducible circuit will be used to eliminate the antibiotics in the rAAV production stage.

## Slide 5
Design of Tet-on/off inducible circuits
Optimization of gene-level and dynamics by engineered inducible variants, Kozak, and Degron tags
Crispr-Cas9 platform development and testing AAVS1, CCR5 and ROSA26 loci
AAV parts integration, The baseline of Stable cell line
Testing inducible plasmids via transient
Analytical methods (qPCR, Elisa, RT-qPCR, WB, proteomics)
Tet off/on switch for 3 cassettes via Golden gate
Transfer plasmid
Assembly plasmid
Replication plasmids
Udel
inducible design and plasmid assembly
UML
Crisp-cas9, cell culture, integration
Evaluate optimized plasmids via transient
Optimized AAV parts integration, The optimized stable cell line
UML & UD
Research Workflow & Timeline
4-8 M
9-14 M
1-3 M

## Slide 6: UD Progress

## Slide 7
Plasmid Design

## Slide 8
Plasmid Design
Addition of PhiC31 integrase on assembly plasmid to exchange serotypes in future

## Slide 9
Plasmid Design
Silencing of internal p19 promoter through removal of start codon to stop transcription of Rep52/40
Is this sufficient to silence p19?
Chejanovsky, N.; Carter, B. J. Mutagenesis of an AUG Codon in the Adeno-Associated Virus Rep Gene: Effects on Viral DNA Replication. Virology 1989, 173 (1), 120–128. https://doi.org/10.1016/0042-6822(89)90227-4.

## Slide 10
Plasmid Design
Bxb1 sites moved inside ITRs for ease of cloning/payload exchange

## Slide 11
Fragment Design
 | Rep78/68
Sequence Change (AA) | 225: ATG → GGG
Reason | Removal of p19 start codon
Comments | Previous work reported the silencing of the p19 promoter through the mutation of the start codon1
(1) Chejanovsky, N.; Carter, B. J. Mutagenesis of an AUG Codon in the Adeno-Associated Virus Rep Gene: Effects on Viral DNA Replication. Virology 1989, 173 (1), 120–128. https://doi.org/10.1016/0042-6822(89)90227-4.

## Slide 12
Plasmid Assembly Timeline
 | Assembly Plasmid | Replication Plasmid | Transfer Plasmid
Designing | 02/10 - 03/29 | 02/10 - 03/29 | 02/10 - 03/02
Ordering | 03/02 - 04/11 | 03/02 - 04/11 | 03/02 - 3/15
Entry Vector Preparations | 03/15 - 4/25 | 03/15 - 4/25 | 03/15 - 4/25
Golden Gate Assembly | 04/25-06/22 | 04/25-06/05 | 04/25-present
Version 1

## Slide 13: UML Progress

## Slide 14: Baseline development for AAV inducible producer
Donor plasmids assembly
sgRNA design
Cloning sgRNA to Cas9 vector
plasmid sequencing
HEK293 cells transfected with two plasmids & antibiotic selection
Genomic DNA extraction and Site-specific integration testing via junction PCR
Stable cell pool
SSI pool and single clones
Replication plasmid
Assembly plasmid
Transfer plasmid
Cell sorter
Notes: The same workflow. We need to reassemble the donor plasmid.

## Slide 15: AAV Replication donor plasmid Gibson 1-- Connect replication and AAVS1 HA
Gibson
Part 2, PmeI & PacI cut 8368bp
Part 1+ part 2
Replication+ AAVS1, 14081bp
Part 1 -- PCR，5700bp

## Slide 16
Part 1+ part 2
Replication+ AAVS1+GFP, 15682bp
Gibson
Part 1 – PmeI cut ，14081bp
Part 2, PCR, 1601bp
Target size 10972bp+4890bp
AAV Replication donor plasmid Gibson 2-- Connect replication+AAVS1HA and GFP(outside HA)

## Slide 17: Whole plasmid sequencing
Theoretical seq
Measured seq
Notes: The same workflow. We need to reassemble the donor plasmid.

## Slide 18: Baseline development for AAV inducible producer
Donor plasmids assembly
sgRNA design
Cloning sgRNA to Cas9 vector
plasmid sequencing
HEK293 cells transfected with two plasmids & antibiotic selection
Genomic DNA extraction and Site-specific integration testing via junction PCR
Stable cell pool
SSI pool and single clones
Replication plasmid
Assembly plasmid
Transfer plasmid
Cell sorter

## Slide 19: Antibiotic selection D8
AAVS1+Replication+ GFP, microscope image, 100*
G418 800ug/mL
Cell clones appear, GFP cells(RI&SSI) and non-GFP(SSI) cells can be seen
Control
Cells dead, no GFP expression

## Slide 20: Site-specific integration strategy
Round 1
Replication cassettes integration
Co-transfect with sgRNA + replication donor plasmid in AAVS1
Round 2
Assembly cassettes integration
Round 3
transgene cassettes integration
Co-transfect with sgRNA + transgene donor plasmid in CCR5
Antibiotic selection for two weeks
Co-transfect with sgRNA + assembly donor plasmid in ROSA26
Antibiotic selection for two weeks
Antibiotic selection for two weeks
Stable cell pool
5’ 3’ Junction PCR
SSI pool 1
RI pool (discard)
Cell sorter
Intermediate QC checkpoints
5’ 3’ Junction PCR
Transient other two plasmids for rAAV production
Single clone via cell sorter for knock-in evaluation (qPCR relative genome copy and junction PCR)
SSI pool 1 for Round 2
Stable cell pool
SSI pool 2
Cell sorter
RI pool (discard)
SSI pool 2 for Round 3
Stable cell pool
SSI pool 3
Cell sorter
RI pool (discard)

## Slide 21
  Triple plasmids transient transfection to produce rAAV
Gene function testing & inducibility testing (tet-off)
Helper+ Rep/Cap+ ITR-GFP
Replication plasmid+ assembly plasmid(tTA)+ ITR-GFP
Replication plasmid+ assembly plasmid(tTA)+ ITR-GFP +500ng/mL Dox
6 well plate Transfection conditions | 
Media working volume | 3mL
Plating Density (total cells) | 5E5
Total DNA amount | 2ug
Plasmid ratio | 1:1:1
PEI:DNA | 1:1
Cocktail volume | 300 uL
Incubation time | 15min
Cocktail media | OptiMEM
HEK293T
Condition 1
HEK293T
Condition 2
HEK293T
Condition 3
HEK293T
Condition 1
HEK293T
Condition 2
HEK293T
Condition 3
Chart: Genome titer(Vg/L)
| 293T ctrl | 293T tTA | 293T tTA _dox500
 | 2.2983e+12 | 462750728210.9713 | 1.6773e+12
The effective concentration range of Dox is 10-1000ng/mL in mammalian cells based on the literature investigation. (doi:10.1038/sj.mt.6300383) (DOI: 10.1002/jgm.3067)
Notes: The same workflow. We need to reassemble the donor plasmid.

## Slide 22: Next Steps
UML
  Replication donor plasmid integration
    Intermediate QC checkpoints.
  Assembly donor plasmid integration
UD
  Finish transfer plasmid cloning and send to UML
  Begin transient transfection tests on version 1 plasmids
  Begin considering future version plasmid designs

## Slide 23
Q1 2023
Design of Tet-on/off inducible circuits (UD)
Crispr-Cas9 platform development and testing AAVS1, CCR5 and ROSA26 loci (UML)
Q2 2023
Tet off/on switch for 2 AAV cassettes via Golden gate. 1, replication plasmid, 2, assembly plasmid(UD)
Q3 2023
Analytical methods (qPCR, Elisa, RT-qPCR, WB, proteomics) (UML/UD)
Testing inducible plasmids via transient (UML/UD)
Q4 2023
2024
Cell line productivity and stability evaluation(UML/UD)
Tet off/on switch for the 3rd AAV cassette via Golden gate, 3, transfer plasmid(UD)
Site-specific integration of the 2nd and 3rd cassette and develop the baseline of stable cells (UML)
Optimized AAV parts integration, The optimized stable cell line(UML)
Optimization of gene level and dynamics by engineered inducible variants, Kozak, and Degron tags (UD)
Site-specific integration of replication cassette made by UD (UML)
Optimization of gene level and dynamics by engineered inducible variants, Kozak, and Degron tags (UD)
Evaluate optimized plasmids via transient(UML/UD)
AAV production bottlenecks investigation(UD/UML)
Other investigations (UML/UD)
Research Sites – Timeline and Milestones